## Action items
ID | Action item | Status (Open/closed) | Sprint closed
Stop 1.1 | By holding eachother acountable and make sure that the person talking is finished speaking | closed
Stop 1.2 | having a final meeting 2 days before the sprint review | closed
Start 1.1 | During a lesson day second monday of the sprint | closed
Start 1.2 | The scrummaster asks people about the progress at the start of the meeting and via chat | closed
Start 1.3 | setting deadlines | closed
Start 1.4 | Starting with testing on monday 2 days before the sprint review | closed
Start 1.5 | start on time | closed
Start 1.6 | first code the part so everybody can continue and then code the parts that dont overlap | closed
Stop 2.1 | Setting event deadlines in the discord as a visual reminder. | closed
Stop 2.2 | Check all your user stories and ask yourself if it's fairly easily doable before the deadlines | closed
Start 2.1 | setting semi-deadlines | closed
Start 2.2 | start on time | closed
Start 2.3 | Starting with testing on monday 2 days before the sprint review | closed
Stop 3.1 | start coding before it's to late | closed
Start 3.1 | testing on monday and until tuesday evening before sprint review the program | closed
Start 3.2 | starting with documentation before the sprint and after the sprint. | open
Stop 4.1 | start coding before it's to late. | closed
Start 4.1 | Start on monday with testing until tuesday in the evening before sprint review. | Closed
Start 4.2 | check each other work | closed
Start 5.1 | check each other work | closed
Start 5.1 | check each other work | closed

## Sprint 0
ID | Stop | Team member | ID | Start | Team member | ID | Continue | Team member
Stop 0.1 |  |  | Start 0.1 |  |  | Continue 0.1
Stop 0.2 |  |  | Start 0.2 |  |  | Continue 0.2
Stop 0.3 |  |  | Start 0.3 |  |  | Continue 0.3
Stop 0.4 |  |  | Start 0.4 |  |  | Continue 0.4
Stop 0.5 |  |  | Start 0.5 |  |  | Continue 0.5
Stop 0.6 |  |  | Start 0.6 |  |  | Continue 0.6
Stop 0.7 |  |  | Start 0.7 |  |  | Continue 0.7
Stop 0.8 |  |  | Start 0.8 |  |  | Continue 0.8
Stop 0.9 |  |  | Start 0.9 |  |  | Continue 0.9
Stop 0.10 |  |  | Start 0.10 |  |  | Continue 0.10
Stop 0.11 |  |  | Start 0.11 |  |  | Continue 0.11
Stop 0.12 |  |  | Start 0.12 |  |  | Continue 0.12
Stop 0.13 |  |  | Start 0.13 |  |  | Continue 0.13
Stop 0.14 |  |  | Start 0.14 |  |  | Continue 0.14
Stop 0.15 |  |  | Start 0.15 |  |  | Continue 0.15
Stop 0.16 |  |  | Start 0.16 |  |  | Continue 0.16
Stop 0.17 |  |  | Start 0.17 |  |  | Continue 0.17
Stop 0.18 |  |  | Start 0.18 |  |  | Continue 0.18
Stop 0.19 |  |  | Start 0.19 |  |  | Continue 0.19
Stop 0.20 |  |  | Start 0.20 |  |  | Continue 0.20

## Sprint 1
ID | Stop | Team member | ID | Start | Team member | ID | Continue | Team member
Stop 1.1 | Let eachother finish speaking | Evan Cheung | Start 1.1 | 1 irl meeting per sprint | kevin troost | Continue 1.1 | having frequent meetings | kevin troost
Stop 1.2 | Stop with doing everthing on the last 2 days | Ramino Vrca | Start 1.2 | communicating your progress | kevin troost | Continue 1.2 | not have meetings in the weekend | kevin troost
Stop 1.3 |  |  | Start 1.3 | setting deadlines and note them in the communication channel | kevin troost | Continue 1.3 | continue to work well together | Ramino Vrca
Stop 1.4 |  |  | Start 1.4 | Start with testing 2 days before the sprint review | Ramino Vrca | Continue 1.4 |  | Mustafa Kuruoglu
Stop 1.5 |  |  | Start 1.5 | Starting with programming earlier in the sprint | Ramino Vrca | Continue 1.5 |  | Tariq Landvreugd
Stop 1.6 |  |  | Start 1.6 | isolating tasks | evan cheung | Continue 1.6
Stop 1.7 |  |  | Start 1.7 |  |  | Continue 1.7
Stop 1.8 |  |  | Start 1.8 |  |  | Continue 1.8
Stop 1.9 |  |  | Start 1.9 |  |  | Continue 1.9
Stop 1.10 |  |  | Start 1.10 |  |  | Continue 1.10
Stop 1.11 |  |  | Start 1.11 |  |  | Continue 1.11
Stop 1.12 |  |  | Start 1.12 |  |  | Continue 1.12
Stop 1.13 |  |  | Start 1.13 |  |  | Continue 1.13
Stop 1.14 |  |  | Start 1.14 |  |  | Continue 1.14
Stop 1.15 |  |  | Start 1.15 |  |  | Continue 1.15
Stop 1.16 |  |  | Start 1.16 |  |  | Continue 1.16
Stop 1.17 |  |  | Start 1.17 |  |  | Continue 1.17
Stop 1.18 |  |  | Start 1.18 |  |  | Continue 1.18
Stop 1.19 |  |  | Start 1.19 |  |  | Continue 1.19
Stop 1.20 |  |  | Start 1.20 |  |  | Continue 1.20

## Sprint 2
ID | Stop | Team member | ID | Start | Team member | ID | Continue | Team member
Stop 2.1 | Stop with doing everthing on the last 2 days | kevin troost | Start 2.1 | Start setting dealines with coding | Ramino Vrca | Continue 2.1 | Continue having frequent meetings | Ramino Vrca
Stop 2.2 | Taking on too many new features per sprint | Tariq Landvreugd | Start 2.2 | Start with programming earlier in the sprint | kevin troost | Continue 2.2 | Continue communicating your progress ESPECIALLY if they overlap with files others are working on | Kevin Troost, Tariq Landvreugd
Stop 2.3 |  |  | Start 2.3 | Start making test 2 days before review | kevin troost | Continue 2.3 | Continue isolating tasks | kevin troost
Stop 2.4 |  |  | Start 2.4 |  |  | Continue 2.4 | fixing small bugs and checking for the small bugs | Mustafa Kuruoglu
Stop 2.5 |  |  | Start 2.5 |  |  | Continue 2.5
Stop 2.6 |  |  | Start 2.6 |  |  | Continue 2.6
Stop 2.7 |  |  | Start 2.7 |  |  | Continue 2.7
Stop 2.8 |  |  | Start 2.8 |  |  | Continue 2.8
Stop 2.9 |  |  | Start 2.9 |  |  | Continue 2.9
Stop 2.10 |  |  | Start 2.10 |  |  | Continue 2.10
Stop 2.11 |  |  | Start 2.11 |  |  | Continue 2.11
Stop 2.12 |  |  | Start 2.12 |  |  | Continue 2.12
Stop 2.13 |  |  | Start 2.13 |  |  | Continue 2.13
Stop 2.14 |  |  | Start 2.14 |  |  | Continue 2.14
Stop 2.15 |  |  | Start 2.15 |  |  | Continue 2.15
Stop 2.16 |  |  | Start 2.16 |  |  | Continue 2.16
Stop 2.17 |  |  | Start 2.17 |  |  | Continue 2.17
Stop 2.18 |  |  | Start 2.18 |  |  | Continue 2.18
Stop 2.19 |  |  | Start 2.19 |  |  | Continue 2.19
Stop 2.20 |  |  | Start 2.20 |  |  | Continue 2.20

## Sprint 3
ID | Stop | Team member | ID | Start | Team member | ID | Continue | Team member
Stop 3.1 | stop waiting till the last day to fix stuff that doesnt work (code) | Mustafa Kuruoglu | Start 3.1 | we should test it better so we dont get errors when we show our product | Mustafa Kuruoglu | Continue 3.1 | Dividing work evenly so we can spread the work out | Tariq Landvreugd
Stop 3.2 |  |  | Start 3.2 | start with doing more documentation | Ramino Vrca | Continue 3.2 | Making events in the Discord | Tariq Landvreugd
Stop 3.3 |  |  | Start 3.3 |  |  | Continue 3.3 | Showing the refinements beforehand for a less cluttered demo | Tariq Landvreugd
Stop 3.4 |  |  | Start 3.4 |  |  | Continue 3.4 | Working well in a team | Ramino Vrca
Stop 3.5 |  |  | Start 3.5 |  |  | Continue 3.5
Stop 3.6 |  |  | Start 3.6 |  |  | Continue 3.6
Stop 3.7 |  |  | Start 3.7 |  |  | Continue 3.7
Stop 3.8 |  |  | Start 3.8 |  |  | Continue 3.8
Stop 3.9 |  |  | Start 3.9 |  |  | Continue 3.9
Stop 3.10 |  |  | Start 3.10 |  |  | Continue 3.10
Stop 3.11 |  |  | Start 3.11 |  |  | Continue 3.11
Stop 3.12 |  |  | Start 3.12 |  |  | Continue 3.12
Stop 3.13 |  |  | Start 3.13 |  |  | Continue 3.13
Stop 3.14 |  |  | Start 3.14 |  |  | Continue 3.14
Stop 3.15 |  |  | Start 3.15 |  |  | Continue 3.15
Stop 3.16 |  |  | Start 3.16 |  |  | Continue 3.16
Stop 3.17 |  |  | Start 3.17 |  |  | Continue 3.17
Stop 3.18 |  |  | Start 3.18 |  |  | Continue 3.18
Stop 3.19 |  |  | Start 3.19 |  |  | Continue 3.19
Stop 3.20 |  |  | Start 3.20 |  |  | Continue 3.20

## Sprint 4
ID | Stop | Team member | ID | Start | Team member | ID | Continue | Team member
Stop 4.1 | stop writing code on the last 2 days.(only small fixes) | Ramino Vrca | Start 4.1 | start with testing 2 days before the sprint review | Ramino Vrca | Continue 4.1 | Setting deadlines on a specific day and time | Tariq Landvreugd
Stop 4.2 |  |  | Start 4.2 | Start on time | Kevin troost | Continue 4.2 | Making events to remind us when these deadlines are | Tariq Landvreugd
Stop 4.3 |  |  | Start 4.3 |  |  | Continue 4.3 | Having frequent meetings | Tariq Landvreugd
Stop 4.4 |  |  | Start 4.4 |  |  | Continue 4.4 | dividing more work among us so we can finish more | Mustafa Kuruoglu
Stop 4.5 |  |  | Start 4.5 |  |  | Continue 4.5
Stop 4.6 |  |  | Start 4.6 |  |  | Continue 4.6
Stop 4.7 |  |  | Start 4.7 |  |  | Continue 4.7
Stop 4.8 |  |  | Start 4.8 |  |  | Continue 4.8
Stop 4.9 |  |  | Start 4.9 |  |  | Continue 4.9
Stop 4.10 |  |  | Start 4.10 |  |  | Continue 4.10
Stop 4.11 |  |  | Start 4.11 |  |  | Continue 4.11
Stop 4.12 |  |  | Start 4.12 |  |  | Continue 4.12
Stop 4.13 |  |  | Start 4.13 |  |  | Continue 4.13
Stop 4.14 |  |  | Start 4.14 |  |  | Continue 4.14
Stop 4.15 |  |  | Start 4.15 |  |  | Continue 4.15
Stop 4.16 |  |  | Start 4.16 |  |  | Continue 4.16
Stop 4.17 |  |  | Start 4.17 |  |  | Continue 4.17
Stop 4.18 |  |  | Start 4.18 |  |  | Continue 4.18
Stop 4.19 |  |  | Start 4.19 |  |  | Continue 4.19
Stop 4.20 |  |  | Start 4.20 |  |  | Continue 4.20

## Sprint 5
ID | Stop | Team member | ID | Start | Team member | ID | Continue | Team member
Stop 5.1 | Starting on the last day with coding | Ramino Vrca | Start 5.1 | Starting with coding earlier in the sprint. | Ramino Vrca | Continue 5.1 | having meetings | Mustafa Kuruoglu
Stop 5.2 |  |  | Start 5.2 |  |  | Continue 5.2 | dividing work evenly | Mustafa Kuruoglu
Stop 5.3 |  |  | Start 5.3 |  |  | Continue 5.3 | continue to work well together | Kevin troost
Stop 5.4 |  |  | Start 5.4 |  |  | Continue 5.4
Stop 5.5 |  |  | Start 5.5 |  |  | Continue 5.5
Stop 5.6 |  |  | Start 5.6 |  |  | Continue 5.6
Stop 5.7 |  |  | Start 5.7 |  |  | Continue 5.7
Stop 5.8 |  |  | Start 5.8 |  |  | Continue 5.8
Stop 5.9 |  |  | Start 5.9 |  |  | Continue 5.9
Stop 5.10 |  |  | Start 5.10 |  |  | Continue 5.10
Stop 5.11 |  |  | Start 5.11 |  |  | Continue 5.11
Stop 5.12 |  |  | Start 5.12 |  |  | Continue 5.12
Stop 5.13 |  |  | Start 5.13 |  |  | Continue 5.13
Stop 5.14 |  |  | Start 5.14 |  |  | Continue 5.14
Stop 5.15 |  |  | Start 5.15 |  |  | Continue 5.15
Stop 5.16 |  |  | Start 5.16 |  |  | Continue 5.16
Stop 5.17 |  |  | Start 5.17 |  |  | Continue 5.17
Stop 5.18 |  |  | Start 5.18 |  |  | Continue 5.18
Stop 5.19 |  |  | Start 5.19 |  |  | Continue 5.19
Stop 5.20 |  |  | Start 5.20 |  |  | Continue 5.20